## Slide 1
GPN SRE | Engineering
AI-Assisted RCA Capability
Disputes Journey - Revised Project Plan
Owner: Nayeem Khan Status: v1.0 - Revised from PO draft, restructured to 6 phases
Scope: Disputes Journey, 1 endpoint (MVP)
Timeline: April - December 2026
Internal - Capital One

## Slide 2
What changed from the original plan, and why
The original 3-phase plan from Product is a solid starting point. Here's what I'm changing based on how these projects actually play out.
Original PO Plan (3 phases)
Phase 1 - Scope & Design
Phase 2 - Data Access & Compliance
Phase 3 - Data Validation & Integration
Phase 4 - Build, Validate & Demo
Gaps I see:
• Bundles Build + Validate + Demo into one phase
• No phase for telemetry audit before build
• No ops handoff - who runs this after demo?
• Two phases labeled 'Phase 2'
Revised SRE Plan (6 phases)
1. Scope, Architecture & Alignment
2. Data Access, Compliance & Telemetry Audit
3. Build - Correlation Engine
4. Build - AION Integration
5. Validation Against Historical Incidents
6. Demo, Hardening & Ops Handoff
Why 6 instead of 3:
• Validation gets its own phase - it's where we earn trust
• Correlation and AION are separated - different risks
• Telemetry audit added up front - can't correlate what we don't collect
• Ops handoff is real work, not an afterthought
2

## Slide 3
AI-Assisted RCA - Milestone Timeline
Now
Next
Later
April
May
June
July
August
September
October
November
December
Today
Phase 1 - Scope, Architecture & Alignment
Phase 2 - Data Access, Compliance & Telemetry Audit
Phase 3 - Build: Correlation Engine
Phase 4 - Build: AION Integration
Phase 5 - Validation Against Historical Incidents
Phase 6 - Demo, Hardening & Ops Handoff
Risks
Cyber access delay → Phase 2 slip
Telemetry gaps → weak RCA accuracy
AION integration moving target
Dependencies
SME input (COF + DFS)
NCR + Cyber approvals
AION platform readiness
Architecture sign-off (Andrew + Ben)
Key Decisions
MVP: 1 journey, 1 endpoint
70% RCA accuracy threshold
Validation on real incidents only
3

## Slide 4
Phase detail - what's in scope, what's at risk
Phase 1
Scope, Architecture & Alignment
Apr - mid May (4 wks)
Work:
Lock MVP scope. Finalize architecture (Client→Gateway→Services→DB). Jira epics. AION integration contract draft.
Watch:
Architecture diagram still in progress - blocks everything downstream
Phase 2
Data Access, Compliance & Telemetry Audit
May - end July (12 wks)
Work:
NCR + Cyber approvals for Datadog, Splunk, ServiceNow. Telemetry audit - find instrumentation gaps before build.
Watch:
Cyber approvals unpredictable. If telemetry covers < 80%, scope may need rework.
Phase 3
Build - Correlation Engine
Jul - Aug (6 wks)
Work:
Ingest logs + traces + alerts. Correlate by span ID and timestamp. Apply signal/noise rules.
Watch:
Alert noise higher than expected → tune rules before AION integration.
Phase 4
Build - AION Integration
Aug - Sep (4 wks)
Work:
Wire correlation output to AION. Handle payloads, latency, timeouts. Build SRE-facing output (ServiceNow or AION UI).
Watch:
AION rate limits or latency at incident volume - validate early.
Phase 5
Validation Against Historical Incidents
Sep - Oct (6 wks)
Work:
Run against 15–20 past P1/P2 incidents. Accuracy check + qualitative review by on-call SREs. Tune rules.
Watch:
If < 70% accuracy after tuning, delay demo. Don't demo something we can't stand behind.
Phase 6
Demo, Hardening & Ops Handoff
Nov - Dec (8 wks)
Work:
Stakeholder demo on real incidents. Productionize. Runbooks. Ownership & monitoring for the RCA tool itself.
Watch:
Ops handoff gets deprioritized after demo - I'm protecting this time.
4

## Slide 5
How we'll know it's working
Before we call this MVP done - all of these need to be true. Not some, all.
< 5 min
RCA hypothesis after P1 opens
≥ 70%
Accuracy vs. historical RCAs
< 2%
Data loss in correlation layer
2+
SREs sign off on usefulness
The non-numeric ones (equally important):
Demo runs on real historical incidents - not synthetic test data
Output is readable in under 10 seconds by an on-call engineer
Known failure modes are documented - we're honest about what this doesn't handle well
Ops ownership is defined - someone owns running this after Phase 6
Scope hasn't crept - still one journey, one endpoint
5

## Slide 6
What I need from each of you
Product Owner
Sign off on the revised 6-phase scope by end of Week 1. Attend the demo in Phase 6.
By May 2
AION Team
Named technical contact who can make integration decisions. Written integration contract before Phase 3 starts.
By May 16
Architecture (Andrew + Ben)
Finalized journey architecture diagram (Client → Gateway → Services → DB).
End of Week 1
Cyber / NCR
SLA on approval requests. API documentation for Datadog + Splunk access that's currently not shared.
Phase 2 kickoff
DFS + COF Leadership
Alignment on the 'Disputes only, 1 endpoint' MVP scope. If you want more, we need to discuss timeline impact.
End of Phase 1
Disputes SRE Team
2–3 engineers available in Phase 5 to review output honestly - did this actually help or not?
Sep onwards
I'll drive this. I need you to unblock me when I ask. That's the deal.
6