AI-Assisted Root Cause Analysis (RCA) Capability

Disputes Journey - SRE Engineering Project Plan

# 1. Executive Summary

The Disputes SRE team is seeing inconsistent incident resolution times across platforms despite individual improvements. Our current tooling requires engineers to manually correlate logs, traces, and alerts during an incident - this is slow, error-prone, and doesn't scale as our platform complexity grows.

This project delivers an AI-assisted RCA capability that correlates Datadog traces, logs, and incident data to automatically surface a root cause hypothesis at incident time. The goal isn't to replace the on-call engineer's judgment - it's to cut the time they spend hunting through telemetry so they can focus on resolution and communication.

Based on what we've already seen in our best-case scenarios, this has the potential to push outage reduction from 78% to over 80% and bring average incident duration below 55 minutes. More importantly, it addresses the consistency gap - today, improvements are platform-dependent and we still require manual triage for every incident.

# 2. Problem Statement & Motivation

## 2.1 Current State - Where We Are Today

After a serious look at our incident data, here's the honest picture:

| Metric | Current | Target (MVP) |
| --- | --- | --- |
| Outage Reduction | 78% (avg) | > 80% consistent |
| Incident Duration | ~55–80 min (varies) | < 55 min (P75) |
| RCA Process | 100% manual | AI-assisted hypothesis |
| Cross-platform consistency | Not consistent | Standardized triage path |
| Anomaly detection | Not in place | Signal/noise rules defined |
| Log/trace correlation | None (manual grep) | Automated correlation layer |

## 2.2 Why This Matters Now

- Manual RCA during high-severity incidents is a distraction - engineers are looking at logs instead of mitigating impact

- Our best-case improvement (80%, sub-55min) isn't reproducible because there's no automated process backing it up

- As the Disputes journey scales, this problem gets worse, not better

- Peer SRE teams are starting to adopt AI-assisted tooling - we need to catch up and establish our own baseline

# 3. Success Criteria

## 3.1 MVP Definition of Done

For this MVP to be considered complete and shippable, all of the following must be true:

- RCA hypothesis generated within 5 minutes of a P1/P2 incident being opened in ServiceNow

- Hypothesis correctly identifies the impacted service in ≥ 70% of test cases against historical incidents

- Correlation layer ingests logs + traces + alerts from Datadog with < 2% data loss

- Signal/noise rules reduce alert fatigue by ≥ 30% compared to current state

- Working demo validated against real past high-severity incidents (DFS + COF coverage)

- Output reviewed and signed off by at least 2 on-call SREs from the Disputes team

- AION interface implemented and accessible to SRE team

## 3.2 What This MVP Is NOT

Setting scope expectations early saves rework:

- This is not a full autonomous remediation system - the AI surfaces hypotheses, humans make decisions

- This is not a replacement for runbooks or post-incident reviews

- This is not covering all journeys - scope is locked to Disputes, 1 endpoint for MVP

- This is not a real-time anomaly detection platform - that's a future phase if this proves value

# 4. Technical Approach & Architecture

## 4.1 High-Level Architecture

The architecture has three layers that need to work together:

- Ingestion Layer: Pull structured telemetry from Datadog (traces, logs, metrics) + alert data from Splunk + incident context from ServiceNow

- Correlation Engine: Map traces to logs by span ID and timestamp, correlate against open incidents, apply signal/noise filtering rules

- RCA Generation: Feed correlated context into AION to generate a ranked list of probable root causes + impacted services

- SRE Interface: Surface the hypothesis in a consumable format - either inline in the incident ticket or via AION dashboard

## 4.2 Data Flow (Client → Gateway → Services → DB)

We're mapping the full request path for the Disputes journey through:

- Client request entry point

- API Gateway layer (auth, routing)

- Core Disputes service(s)

- Downstream dependencies (payment processor, DB, third-party integrations)

This map is the foundation for the correlation logic - without it, we're just pattern-matching on noise. This work is in progress with architecture input from the team and needs to be locked before Phase 2 begins.

## 4.3 Signal vs. Noise Rules

One of the biggest risks to RCA accuracy is alert noise. We'll define rules to filter out:

- Flapping alerts (fire/resolve within < 2 min)

- Known false positives from existing monitoring gaps

- Alerts on non-Disputes services that appear correlated but aren't causal

These rules will be reviewed by the team and versioned. Starting with a conservative list and expanding based on feedback from the demo.

# 5. Phase 1 - Scope, Alignment & Design

## Objective

Lock the MVP scope, validate the technical approach, and make sure every team touching this project - AION, Cyber, Compliance, Product - is aligned before we write a line of code.

## Key Activities

- Convert the initiative to Jira: initiative created (done), epics being broken out (in progress)

- Lock MVP scope: Disputes Journey, 1 endpoint, defined success criteria above

- Map the end-to-end journey (Client → Gateway → Services → DB) with architecture team

- Define data flow, system dependencies, APIs, and DB connections involved

- Engage AION team early - get clarity on integration contract before Phase 2

- Loop in Cyber and Compliance at the start, not after the fact

## Deliverables

- MVP scope document (this plan, countersigned by PO and SRE lead)

- Journey architecture diagram with data flow annotated

- Data source inventory (what we need, where it lives, who owns it)

- Initial integration approach with AION documented

- Jira epics and stories mapped to phases

## Dependencies

- SME input from COF individuals and DFS team - need their incident context to validate the journey map

- Architecture input from the team (work in progress) - this is a blocker for Phase 2 start

- Leadership alignment on scope and timeline - need sign-off before proceeding

## Blockers & Risks

- BLOCKER: No defined architecture yet - cannot finalize data flow without it

- BLOCKER: Informal intake process with AION team - need a formal integration contract

- RISK: Scope creep - there will be pressure to add more journeys or features; hold the line on MVP

- RISK: Misalignment on priorities between SRE and Product - resolve in Phase 1 or it compounds in Phase 2

# 6. Phase 2 - Data Access, Compliance & Integration

## Objective

Get the data we need to build this, within the guardrails we have to operate in. Compliance and access management at Capital One aren't optional - we do this right or we don't do it at all.

## Key Activities

- Define data access paths for Datadog, Splunk, and ServiceNow - document what APIs/endpoints we're using and at what frequency

- Build integration roadmap: sequence of access requests, approval timelines, and fallback options if access is delayed

- File and track NCR + Cyber approvals - assign an owner for each approval track, don't let this sit

- Validate data completeness: confirm logs and traces are being captured end-to-end for the Disputes journey

- Identify telemetry gaps: if traces aren't instrumented at a service, flag it now - we can't correlate what we don't have

- Lock the AION integration approach: API contract, payload format, latency requirements, error handling

## Deliverables

- Approved data access for all three platforms (Datadog, Splunk, ServiceNow)

- Compliance-aligned architecture - Cyber/NCR reviewed and signed off

- Integration-ready environment: sandbox/dev environment wired up for Phase 3 development

- Data completeness report: known gaps documented with mitigation plan

## Dependencies

- Cyber/NCR approval timelines - these are often unpredictable; start the process in Week 1 of this phase

- Cyber sharing API documentation for Datadog and Splunk access - currently blocked, escalation path needed

- Telemetry instrumentation completeness - if gaps exist, engineering teams need to instrument before we can proceed

## Blockers & Risks

- BLOCKER: Cyber not sharing documentation - this will delay integration work; need escalation to management if unresolved by Week 5

- BLOCKER: Limited telemetry in some services - RCA accuracy is directly tied to data coverage

- RISK: Data access approval delayed → project stalls; mitigation is to start approvals in Phase 1 in parallel

- RISK: Datadog API rate limits affecting correlation at incident volume - need to validate limits against our P1 incident frequency

- RISK: Incomplete data → misleading RCA hypotheses - better to delay than to demo on bad data

# 7. Phase 3 - Build, Validate & Demo RCA Capability

## Objective

Build the correlation engine and RCA generation layer, validate it against real incidents, and deliver a demo that leadership and stakeholders can see in action. No smoke and mirrors - this runs on actual past incidents from DFS and COF.

## Key Activities

Build Phase (Weeks 8–10)

- Build correlation layer: ingest logs + traces + alerts from Datadog, correlate by span ID and timestamp window

- Implement signal/noise filtering: apply rules defined in Phase 1, tune against historical incidents

- Integrate with AION: pass correlated context, receive RCA hypothesis + impacted service list

- Implement AION interface for SRE consumption (incident ticket enrichment or dashboard view)

Validate Phase (Weeks 11–12)

- Run against historical high-severity incidents (minimum 10 P1/P2 incidents from past 6 months)

- Validate accuracy: does the hypothesis match the actual RCA from the post-incident review?

- Validate usefulness: would this have helped the on-call engineer during the incident? (qualitative review with 2+ SREs)

- Tune signal/noise rules based on validation output

- Document failure modes: what types of incidents does this handle poorly? Be honest about limitations.

Demo Phase (Week 13)

- Conduct demo with DFS + COF stakeholders and leadership

- Walk through 2–3 real incident scenarios with the tool running live

- Present accuracy metrics and known limitations transparently

- Capture feedback and document Phase 2 backlog items

## Deliverables

- Working RCA MVP - production-grade code, not a prototype

- Validation report: accuracy and usefulness scores against historical incidents

- Signal/noise rules documented and versioned

- Demo-ready solution with stakeholder presentation

- Phase 2 backlog: what we learned and what we'd improve next

## Dependencies

- Data readiness from Phase 2 - Phase 3 cannot start without approved, validated access

- AION platform availability and integration contract from Phase 2

- Access to historical incident data for validation - need ServiceNow export of past P1/P2s

## Blockers & Risks

- BLOCKER: AION integration not finalized in Phase 2 - this must be resolved before build starts

- BLOCKER: No anomaly detection baseline - we need to establish what 'normal' looks like per service before we can flag deviations

- RISK: Alert noise makes correlation unreliable - mitigation is the signal/noise rules; if noise is too high at validation, delay demo

- RISK: Historical incident data incomplete or not representative - validate data quality before investing in the full build

# 8. Risk Register & Escalation Path

These are the risks I'm actively watching. Each one has a mitigation and an escalation trigger.

| Risk | Phase | Likelihood | Mitigation | Escalation Trigger |
| --- | --- | --- | --- | --- |
| Cyber access delayed | Phase 2 | High | Start approvals in Phase 1, assign dedicated owner | No response in 5 business days → escalate to SRE Manager |
| AION integration unclear | Phase 1–2 | High | Require formal integration contract before Phase 2 closes | Not resolved by end of Week 4 → escalate to AION leadership |
| Telemetry gaps in Disputes services | Phase 2 | Medium | Gap analysis in Phase 2, instrument missing services | Gaps affect > 20% of Disputes traffic → reassess MVP scope |
| RCA accuracy below threshold (< 70%) | Phase 3 | Medium | Tune signal/noise rules, expand historical validation set | Accuracy < 60% after tuning → delay demo, review architecture |
| Scope creep beyond MVP | All Phases | High | Scope locked in Phase 1, changes require PO + SRE Lead sign-off | Any scope addition → impact assessment + leadership alignment required |

# 9. Assumptions & Out of Scope

## Assumptions

- Datadog is already instrumented for the Disputes journey - if traces are missing, timeline shifts

- AION platform is available and the team has capacity to support integration in Phase 2–3 timeframe

- Historical incident data (P1/P2 last 6 months) is accessible from ServiceNow for validation

- NCR and Cyber approvals can be completed within a 3-week window if started promptly

- Leadership alignment is achievable in Phase 1 - if this is contested, we should resolve it before writing code

## Out of Scope (MVP)

- Multi-journey coverage - Disputes only for MVP

- Real-time anomaly detection and alerting

- Autonomous remediation or auto-rollback

- Integration with change management (SNOW change records)

- Custom ML model training - using AION's existing capability